## Issues Log
22 | Task | Description | Assigned To | Time Estimate (days) | Priority | Status | Comments
3 | Create Entities |  | Sue | 0.5 | 10 | Complete
7 | Set up solution | Create projects for Xyz.Core, Xyz.Dao, Xyz.Windows. Set up UI framework | John | 2 | 10 | Complete
8 | SVN, Project page | Set up SVN, project folders, SharePoint, project page | Sue | 1 | 10 | Complete
5 | Add Concurrency Management |  | Sue | 3 | 20 | Complete
1 | Build Dao | Create NHibernate dao classes for entities and main database. | John | 4 | 20 | Complete
13 | Insert logging |  | John | 0.5 | 20 | Complete
9 | Main layout |  | Sue | 1 | 30 | Complete
12 | Create login |  | Sue | 1 | 30 | Complete
6 | Add validation to entities | Validation checking when saving | Sue | 2 | 40 | Complete
10 | Validation display | Display validation errors to users | John | 2 | 40 | Complete
11 | Report navigation and selection |  | John | 1 | 40 | Complete
2 | XYZ tracking report | Create report for tracking xyx | Sue | 1 | 50 | Complete
14 | Add error wrapper |  | John | 1 | 50 | In progress
15 | ...another task... |  | Sue | 0.75 | 50 | In progress
4 | ...another task... |  |  | 2 | 60
16 | ...another task... |  |  | 1 | 60
17 | ...another task... |  |  | 1 | 60
18 | ...another task... |  |  | 0.5 | 70
19 | ...another task... |  |  | 1.5 | 70
20 | ...another task... |  |  | 0.5 | 70
21 | ...another task... |  |  | 0.5 | 70

## Iteration 1
| Iteration 1 | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2010-10-12 | [5 empty] | 0 | 28 | 27.75 |  |  |  |  | 0 | 0 |  | New Years | 2010-01-03 | 2010-10-28 | Change this with =Today()
| End Date | 2010-11-08 |  |  |  |  | 2010-10-12 | 1 | 26.6 | 27.75 | 0 | 0 |  |  | 0 | 2 | 0 | Family Day | 2010-02-12
| # of Developers | 2 |  |  |  |  | 2010-10-13 | 2 | 25.2 | 27.25 | 0 | 0.5 |  |  | 0.5 | 4 | 0.13 | Good Friday | 2010-04-22
| Efficiency Factor | 0.7 |  |  |  |  | 2010-10-14 | 3 | 23.8 | 25.25 | 2 | 0 |  |  | 2.5 | 6 | 0.42 | Easter Monday | 2010-04-24
| Work Days Total | 20 |  |  |  |  | 2010-10-15 | 4 | 22.4 | 25.25 | 0 | 0 |  |  | 2.5 | 8 | 0.31 | Victoria Day | 2010-05-23
| Dev Days Total | 40 |  |  |  |  | 2010-10-18 | 5 | 21 | 24.25 | 0 | 1 |  |  | 3.5 | 10 | 0.35 | Canada Day | 2010-07-01
| # of Task Work Days | 28 |  |  |  |  | 2010-10-19 | 6 | 19.6 | 21.25 | 0 | 3 |  |  | 6.5 | 12 | 0.54 | Labour Day | 2010-09-05
| m - Ideal Task Days Left | -1.4 |  |  |  |  | 2010-10-20 | 7 | 18.2 | 16.75 | 4.5 | 0 |  |  | 11 | 14 | 0.79 | Natal Day | 2010-10-01
| b - Ideal Task Days Left | 28 |  |  |  |  | 2010-10-21 | 8 | 16.8 | 15.75 | 0 | 1 |  |  | 12 | 16 | 0.75 | Thanksgiving | 2010-10-10
| m - Dev Days Used | 2 |  |  |  |  | 2010-10-22 | 9 | 15.4 | 12.75 | 2 | 1 |  |  | 15 | 18 | 0.83 | Christmas | 2010-12-26
| b - Dev Days Used | 0 |  |  |  |  | 2010-10-25 | 10 | 14 | 11.75 | 1 | 0 |  |  | 16 | 20 | 0.8 | Boxing Day | 2010-12-27
[7 empty] | 2010-10-26 | 11 | 12.6 | 9.75 | 0 | 2 |  |  | 18 | 22 | 0.82
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status | 2010-10-27 | 12 | 11.2 | 8.75 | 0 | 1 |  |  | 19 | 24 | 0.79
3 | Create Entities | 0.5 | Complete | 0.5 | Create Entities | Complete | 2010-10-28 | 13 | 9.8
7 | Set up solution | 2 | Complete | 2 | Set up solution | Complete | 2010-10-29 | 14 | 8.4
8 | SVN, Project page | 1 | Complete | 1 | SVN, Project page | Complete | 2010-11-01 | 15 | 7
5 | Add Concurrency Management | 3 | Complete | 3 | Add Concurrency Management | Complete | 2010-11-02 | 16 | 5.6
1 | Build Dao | 4 | Complete | 4 | Build Dao | Complete | 2010-11-03 | 17 | 4.2
13 | Insert logging | 0.5 | Complete | 0.5 | Insert logging | Complete | 2010-11-04 | 18 | 2.8
9 | Main layout | 1 | Complete | 1 | Main layout | Complete | 2010-11-05 | 19 | 1.4
12 | Create login | 1 | Complete | 1 | Create login | Complete | 2010-11-08 | 20 | 0
6 | Add validation to entities | 2 | Complete | 2 | Add validation to entities | Complete
10 | Validation display | 2 | Complete | 2 | Validation display | Complete
11 | Report navigation and selection | 1 | Complete | 1 | Report navigation and selection | Complete
2 | XYZ tracking report | 1 | Complete | 1 | XYZ tracking report | Complete
14 | Add error wrapper | 1 | In progress | 1 | Add error wrapper | In progress
15 | ...another task... | 0.75 | In progress | 0.75 | ...another task... | In progress
4 | ...another task... | 2 |  | 2 | ...another task...
16 | ...another task... | 1 |  | 1 | ...another task...
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 27.75
| Available Time - Assigned time | 0.25
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W100)
Note on A14: Add the task ID's below